WAPA (RMR) LGIP PHASES, DEPOSITS AND TIMELINES

(WILL BE MODIFIED TO REFLECT ANY FUTURE REVISIONS TO THE LGIP)

| MAJOR LGIP PHASES | PARTY RESPONSIBLE | IC $ DEPOSIT | TIMELINE | COMMENTS |
| --- | --- | --- | --- | --- |
| Valid Interconnection Request | Interconnection Customer (IC) | $10,000 or $20,000 w/o proof of Site Control | After required information is provided | WAPA will identify any deficiencies |
| Scoping Meeting | WAPA to arrange | n/a | + 10 Calendar Days | Review alternates |
| Feasibility Study Agreement | Signed by both parties | +$10,000 | + 45 Calendar Days | Initiates study. IC pays actual cost. |
| System Impact Study Agreement | Signed by both parties | +$50,000 | + 90 Calendar Days | Initiates study. IC pays actual cost. |
| Interconnection Facilities Study Agreement | Signed by both parties | +$100,000 | + 90 or 180 Calendar Days | Initiates study. IC pays actual cost. |
| Environmental Agreement | Signed by both parties | EA +$50,000 to $100,000 EIS + $150,000 to $300,000 | EA 6 to 12 months EIS 12 to 18 months | Initiates study. IC pays actual cost. |
| Large Generator Interconnection Agreement | Negotiated and signed by Both parties. | + $250,000 | Dependent on negotiations. | Network upgrades and interconnection facilities agreed to. LGIA initiates final engineering design and construction. |
| Project Completion | As agreed to by parties | n/a | Dependent upon scope of project. | IC pays actual costs of all facilities required for project. |