## Interconnection Requests
Last Updated 5/8/2018 KNK
Queue Number |  | Request Date | Max Summer MW Output | Max Winter MW Output | Location | Interconnection Facility | COD | Facility Type | Status
070302000001 | Q01 | 2007-03-02 | 200 | 200 | Beaver City, Utah | (I) IPP 345kV Switchyard | 2011-03-01 | Wind | Withdrawn by TP on 5-19-15.
070302000002 | Q02 | 2007-03-02 | 200 | 200 | Beaver City, Utah | (I) IPP 345kV Switchyard | 2011-07-01 | Wind | Withdrawn by TP on 5-19-15.
070910000000 | Q03 | 2007-09-10 | 250 | 250 | Kern County, CA | (DWP) Barren Ridge 230 kV Sw Station | 2014-05-01 | Solar | Project assigned to DWP. Interconnection Facilities have been completed.
080214000000 | Q05 | 2008-02-14 | 300 | 300 | Kern County, CA | Barren Ridge - Castaic 230kV Line | 2016-11-01 | Wind | Interconnection Request Withdrawn (non-responsive)
080317000001 | Q06 | 2008-03-12 | 300 | 300 | Baker, CA | (M) Marketplace-Adelanto 500kV Line | 2013-03-01 | Solar | Reduced Project size to 300 MW. LGIA tendered
080930000000 | Q07 | 2008-09-30 | 300 | 300 | California City, CA | Barren Ridge 230 kV Sw Station | 2016-10-31 | Solar | Interconnection Request withdrawn
090326000000 | Q08 | 2009-03-26 | 150 | 150 | Boulder City, NV | (J) McCullough 230kV Substation | 2014-08-01 | Solar | Feasibility Study Completed
091105000000 | Q09 | 2009-11-03 | 200 | 200 | Owens Valley, CA | (DWP) Owens Gorge - Rinaldi 230kV Line | 2016-12-31 | Solar | Interconnection Request Withdrawn by TP on 3-12-15
100122000000 | Q10 | 2010-01-22 | 90 | 90 | California City, CA | Barren Ridge 230 kV Sw Station | 2016-04-01 | Solar | IR withdrawn per IC request on 2-7-13
100301000000 | Q11 | 2010-03-01 | 60 | 60 | Kern County, CA | Barren Ridge 230 kV Sw Station | 2015-06-30 | Solar | COD on 8/23/16
100615000002 | Q13 | 2010-06-15 | 150 | 150 | Kern County, CA | Owens Gorge - Rinaldi 230kV Line | 2016-09-01 | Solar | Withdrawn per IC request.
101007000000 | Q15 | 2010-10-07 | 100 | 100 | Kern County, CA | (DWP) Owens Gorge - Rinaldi 230kV Line | 2016-07-01 | Solar | Interconnection Request withdrawn
101012000000 | Q15A | 2010-10-12 | 150 | 150 | Mojave, CA | (DWP) Pine Tree 230kV Substation | 2018-12-31 | Wind | Interconnection Request withdrawn
101018000000 | Q16 | 2010-10-18 | 199.5 | 199.5 | Hamblin Valley, UT | Gonder - Intermountain 230kV Line | 2013-11-01 | Wind | Withdrawn by TP on 5-19-15.
101216000000 | Q17 | 2010-12-16 | 250 | 250 | Kern County, CA | Barren Ridge - Rinaldi 230kV Line | 2016-10-31 | Solar | IR withdrawn per IC request
110907000000 | Q18 | 2011-09-07 | 100 | 100 | Kern County, CA | Beacon 230 kV Sw Station | 2016-06-01 | Solar | COD on 7/11/16
110919000000 | Q19 | 2011-09-19 | 250 | 250 | Kern County, CA | Beacon 230 kV Sw Station | 2016-06-01 | Solar | COD on 9/7/16
111003000000 | Q20 | 2011-10-03 | 138 | 138 | Independence, CA | Owens Gorge - Rinaldi 230kV Line | 2014-11-01 | Solar | Withdrawn per IC request on 4-1-15.
111116000000 | Q22 | 2011-11-16 | 200.1 | 200.1 | Barstow, CA | Mead-Victorville 287kV | 2016-03-31 | Wind | Withdrawn per IC on 10-20-14.
111130000000 | Q23 | 2011-11-30 | 243.2 | 243.2 | Victorville, CA | Victorville-Century 287kV Line | 2017-12-15 | Wind | Withdrawn
120217000000 | Q24 | 2012-02-21 | 250 | 250 | Boulder City, NV | (M) Marketplace Substation | 2013-12-31 | Solar | COD on 4/28/15
120314000000 | Q25 | 2012-03-14 | 150 | 150 | Los Angeles County, CA | Barren Ridge - Rinaldi 230kV Line | 2016-12-31 | Solar | Facilities Study completed and report provided to customer on 09/6/17. Customer requested to add to battery storage to its original request on 10/19/17. LADWP is evaluating this request.
120330000000 | Q26 | 2012-03-30 | 150 | 150 | Kern County, CA | Barren Ridge 230 kV Sw Station | 2015-09-01 | Solar | IR withdrawn per IC request on 1-10-13
120417000000 | Q27 | 2012-04-17 | 515 | 515 | Victorville, CA | Victorville-Rinaldi 500 kV line | 2016-12-15 | Solar | Withdrawn per IC request 11-5-13.
120518000000 | Q28 | 2012-05-18 | 150 | 150 | Baker, CA | Mead-Victorville 287kV | 2015-11-01 | Solar | Interconnection Reqeust Withdrawn per IC on 10-17-14
120607000000 | Q29 | 2012-06-07 | 300 | 300 | Boulder City, NV | (J) McCullough 230kV Substation | 2014-09-01 | Solar | Interconnection Request withdrawn
120612000000 | Q30 | 2012-06-12 | 300 | 300 | Rosamond, CA | Barren Ridge - Rinaldi 230kV Line | 2014-04-30 | Solar | Draft Facilities and Harmonic Study report were discussed with the customer. LADWP working on the action items from the discussion.
120726000000 | Q31 | 2012-07-26 | 750 | 850 | Victorville, CA | Victorville Substation | 2015-12-01 | Gas/Steam | Withdrawn per IC request 3-19-14.
120801000000 | Q32 | 2012-08-01 | 200 | 200 | Victorville, CA | Victorville Substation | 2015-10-01 | Solar | Interconnection Request Withdrawn by TP on 12-15-14
120924000000 | Q33 | 2012-09-24 | 180 | 180 | Boulder City, NV | (M) Marketplace Substation | 2014-06-01 | Solar | Interconnection Request withdrawn
121010000000 | Q34 | 2012-10-10 | 200 | 200 | Pearson, CA | Owens Gorge - Barren Ridge 230kV Line | 2014-12-31 | Solar | Interconnection Request Withdrawn
121019000000 | Q35 | 2012-10-19 | 250 | 250 | Clark County, NV | Crystal-Moapa 500kV Line | 2014-02-13 | Solar | COD on 12/8/16
121023000000 | Q36 | 2012-10-23 | 300 | 300 | Lucerne Valley, CA | Mead-Victorville 287kV | 2014-10-01 | Solar | Interconnection Request Withdrawn per IC on 12-17-14
121128000000 | Q37 | 2012-11-28 | 100 | 100 | Boulder City, NV | (M) Marketplace Substation | 2015-04-30 | Solar | Harmonic Study Report being reviewed by MAP Tech Review Comm. MAP/MPP E&O approved the Resolution approving the Harmonic Study Report. Facilities Studyand Harmonic Study report finalized and sent to the customer on 9/29/17. LADWP to tender the LGIA.
121129000000 | Q38 | 2012-11-29 | 470 | 470 | California City, CA | Barren Ridge 230 kV Sw Station | 2014-11-01 | Solar | Withdrawn by TP on 10-21-14.
121129000001 | Q39 | 2012-11-29 | 396 | 396 | California City, CA | Barren Ridge 230 kV Sw Station | 2015-11-01 | Solar | Withdrawn by TP on 10-21-14.
121129000002 | Q40 | 2012-11-29 | 100 | 100 | Kern County, CA | Barren Ridge-Rinaldi 230 kV Line | 2019-09-15 | Solar | Harmonic Study report finalized on 09/05/17. Facilities Study is in progress.
121129000003 | Q41 | 2012-11-29 | 200 | 200 | Baker, CA | Mead-Victorville 287kV | 2016-12-31 | Wind | Interconnection Request Withdrawn per IC on 10-17-14
130402000000 | Q42 | 2013-04-02 | 150 | 150 | Rosamond, CA | Barren Ridge - Rinaldi 230kV Line | 2015-09-01 | Solar | SIS in progress
130618000000 | Q43 | 2013-06-18 | 300 | 300 | Kern County, CA | Beacon 230 kV Sw Station | 2016-08-01 | Solar | Withdrawn by TP on 12-15-14.
130904000000 | Q44 | 2013-09-04 | 300 | 300 | Delta, UT | (I) IPP 345kV Switchyard | 2018-12-31 | Solar | SIS in progress
131204000000 | Q45 | 2013-12-04 | 300 | 300 | Boulder City, NV | (M) Marketplace Substation | 2014-09-30 | Solar | Facilities Study Agreement executed on 09/19/17.
140130000000 | Q46 | 2014-01-30 | 34 | 44 | Mono County, CA | 230 kV Middle Gorge Substation | 2017-01-01 | Geothermal | Withdrawn per IC request dated 4-5-17
150730000000 | Q47 | 2015-07-30 | 200 | 200 | Kern County, CA | Barren Ridge 230 kV Sw Station | 2019-06-01 | Solar | Facilities Study Agreement executed on 08/09/17. Facilities Study ongoing.
150730000001 | Q48 | 2015-07-30 | 200 | 200 | Kern County, CA | Barren Ridge 230 kV Sw Station | 2020-01-01 | Solar | Facilities Study Agreement executed on 11/03/17. Facilities Study ongoing.
150825000000 | Q49 | 2015-08-25 | 300 | 300 | Delta, UT | (I) IPP 345kV Switchyard | 2020-06-01 | Solar | Facilities Study Agreement executed on 11/03/17. Facilities Study ongoing.
160105000000 | Q50 | 2016-01-05 | 400 | 400 | Delta, UT | (I) IPP 345kV Switchyard | 2022-06-01 | Solar | Facilities Study Agreement executed on 11/03/17. Facilities Study ongoing.
160105000001 | Q51 | 2016-01-05 | 400 | 400 | Delta, UT | (I) IPP 345kV Switchyard | 2022-06-01 | Solar | Facilities Study Agreement executed on 11/03/17. Facilities Study ongoing.
160114000000 | Q52 | 2016-01-14 | 324 | 324 | Delta, UT | (I) IPP 345kV Switchyard | 2018-12-31 | Solar | SIS completed.
160728000000 | Q53 | 2016-07-28 | 285 | 285 | Delta, UT | (I) IPP 345kV Switchyard | 2019-06-30 | Solar | SIS in progress
160829000000 | Q54 | 2016-08-29 | 200 | 200 | Indian Wells Valley, CA | Barren Ridge - Cottonwood 230kV Line | 2021-06-01 | Solar | SIS Agmt signed on 7/5/17; SIS in progress
160829000001 | Q55 | 2016-08-29 | 500 | 500 | Indian Wells Valley, CA | Barren Ridge - Cottonwood 230kV Line | 2022-06-01 | Solar | SIS Agmt signed on 7/5/17; SIS in progress
160926000001 | Q56 | 2016-09-26 | 300 | 300 | Inyo County, CA | Inyo 230 kV Switching Station | 2021-06-01 | Solar | SIS Agmt was executed 5/25/17. SIS Ongoing.
170109000001 | Q57 | 2017-01-09 | 850 | 850 | Victorville, CA | Adelanto Substation | 2020-06-01 | CC & Solar | Feasibility Study Agreement executed on 08/30/17. Feasibility study ongoing.
170119000001 | Q58 | 2017-01-19 | 150 | 150 | Rosamond CA | Barren Ridge - Rinaldi 230kV Line | 2021-12-31 | Solar | SIS Agmt was executed 5/25/17, SIS Ongoing.
170308000001 | Q59 | 2017-03-08 | 77 | 77 | Kern CA | Pine Tree 230KV Substation | 2020-12-01 | Solar | SIS Agmt was executed 5/25/17, SIS Ongoing.
170627000000 | Q60 | 2017-06-27 | 65 | 65 | Kern County, CA | Beacon 230 kV Sw Station | 2019-12-31 | BESS | SIS in progress.
170717000000 | Q61 | 2017-07-17 | 250 | 250 | Moapa Indian Reservation, 30 miles North of Las Vegas, NV | 500 kV Moapa-Crystal Gentie | 2021-06-30 | Solar&BESS | Withdrawn per IC request dated 1-16-18
171003000000 | Q62 | 2017-10-03 | 75 | 75 | Carson, CA | 138kV Bus Station C Wlimington | 2017-06-20 | BESS | Application received and validated.
180124000000 | Q63 | 2018-01-19 | 135 | 135 | Kern County, CA | Barren Ridge 230KV Substation | 2020-06-20 | Solar (90MW) BESS (45MW) | IC revised design on 4/16/2018
180319000000 | Q64 | 2018-03-19 | 300 | 300 | Beaver City, Utah | Tab line on Milford Wind Gen-tie | 2020-11-30 | Solar 300MW BESS 150MW | Application received via IPA, setting up scoping meeting on 4/25/18
(J) Other Jointly-Owned Facility
(M) Mead-Adelanto Project Facility
(DWP)- LADWP Project