## Request Listing-2014
Economic Study Request Listing - 2014
Study # | Study Year | Request Recieve Date | Study Request Name | Study Description | Valid /Invalid Economic Request | Type of Study | Date sent to Region or Sub Region | Cluster Status | Request Status | Status | Expected Completion date
1 | 2014 | 2014-02-26 | PPL | South of Great Falls Congestion Project |  | Local | Local Economic Study |  |  | In an Economic request submitted to NWE, PPL states that “[t]he purpose of the South of Great Falls (SOGF) Path Economic Study Request (ESR) is a reliability study to assess existing congestion between the Great Falls Area and the rest of the NorthWestern Energy Transmission System in southbound directions.” In PPL’s Economic Study Request (ESR), PPL suggested a project that would consist of a new 230 kV transmission line connection from Great Falls to Three Rivers. PPL believes this study request would help relieve future congestion created by existing generation projects and the impacts of the Montana Alberta Tie Line (MATL). This ESR is a power flow reliability study on the NorthWestern Energy Transmission System in the south bound direction. This request was reviewed at the 3-20-14 TRANSAC Meeting and deemed a valid request. On May 23rd NorthWestern Energy met with PPL to review and finalize the Local Economic Study Plan. Progress was reviewed at the June 19, 2014 TRANSAC meeting and the September 18, 2014 TRANSAC meeting. On December 3, 2014 the completed Local Economic Study was sent to PPL and on December 4, 2014 the report was posted on NorthWestern's OASIS website. The Local Economic Study request is complete. | Year-end 2014
Updated: 12-10-14

## Contact Info
For questions regarding the Economic Studies please contact:
Don Bauer
Electric Transmission Planning
(406) 497-3542
don.bauer@northwestern.com
or
John Leland
Regional Planning
(406) 497-3383
john.leland@northwestern.com
For RSVP's or questions regarding the meetings please contact:
Kathy Bauer, Analyst
Electric Transmission Planning
(406) 497-3576
kathleen.bauer@northwestern.com