## System Problems
Highest Priority System Problems/Decision Matrix (01/24/13)
|  |  | Consequences of Event |  |  |  |  | Likelihood
System Element/Event | WECC Category (A,B,C,D) | Year Problem Starts | Stability Problems | Thermal Problems/Load Loss | Voltage Problems | Peak Load Affected (MW) | Conseqs Factor | System Condition | Seasonal Condition | Other Exposure Condition | Risk Factor | Expected Conseqs CF x RF | Mitigation Cost ($M) | Expected Conseqs Rank | Mitigation Plan | Comments | Mitigation Complete Year (Est)
Consequences Factor = (Stability + Thermal + Voltage Problems Factor) X Peak Load Affected
Risk Factor = System Cond Factor X Seasonal Cond Factor X Other Condition Factor
Rating Factors |  |  | Stability and Thermal |  | Voltage |  |  | System |  | Seasonal |  | Other
|  |  | Extreme | 10 | Outage | 10 | Out | Normal | 0.9995 | S Peak | 0.12 | Normal | 1 | Occurs under N-0
|  |  | Severe | 5 | Very Low < 80% | 5 | < 80% | Outage1 | 0.0005 | W Peak | 0.12 | Major | 1 | Long Line > 30 miles
|  |  | Moderate | 2 | Low | 2 | < FERC | Outage2 | 5e-05 | SWPeak | 0.25 | Moderate | 0.5 | Medium Line
|  |  | Minor | 1 | High | 2 | > FERC |  |  | Light | 0.25 | Minor | 0.1 | Short Line < X miles
|  |  | None | 0 | None | 0 | OK |  |  | Average | 0.75 | Sub | 0.033 | Substation Equipment
[10 empty] | All | 1
Consequences Notes: |  |  | Extreme: | Regional or statewide impacts, widespread outage
|  |  | Severe: | Divison wide impacts and multiple outages
|  |  | Moderate: | Localized impacts with single outages
|  |  | Minor: | Small area impacts, no outages
|  |  | None: | No problems
COSTS AND MITIGATION ARE PRELIMINARY OR ESTIMATED ONLY FOR EXAMPLE

## Decision Matrix
Decision Rule Matrix
Problem: | Idenify the Problem or event
Mitigation: | Briefly describe the mitigation proposed
|  | Raw | Rank
| Units | Data | Factor | Comment
Consequences of Event | MW Affected | Load | Note 1 | Describe load lost, voltage or thermal problems, etc
Risk of Event | None | Describe problem conditions | Note 2 | Describe under what conditions the problem occurs: normal, outage, load level, seasons affected, etc
Overall Risk | None | Conseq X Risk = | Result
Cost | TPV Rev Req | $ Cost | -- | List major cost components
Solution Duration | Years | Years | -- | Cost/Duration = $/year
Discussion | Any other notes or comments on problem or proposed mitigation.
Note 1: Calculate and enter consequences factor per details on priority matrix
Note 2: Calculate and enter risk factor per details on priority matrix

## Example
Decision Rule Matrix
Problem: | Low Voltage Helena - Three Rivers Area 100 kV System
Mitigation: | Option A: Cap Banks at E Helena, Three Rivers, Broadwater
|  | Raw | Rank
| Units | Data | Factor | Comment
Consequence of event | MW Affected | 53 | 105 | No risk of lost load, but voltages below FERC 715 minimums under normal system conditions, peak load.
Risk | Prob, Freq of event | Occurs now under normal and outage conditions at peak loads | 0.25 | Because problem occurs now under normal system conditions, but only at peak load, risk factor is 25%.
Con. X Risk | None | 105 X .25 | 26.3
Cost | TPV Rev Req | $2.1M | -- | 50 MVAR E Helena, 25 MVAR Three Rivers, 10 MVAR at Broadwater @ $25K/MVAR
Solution Duration | Years | 15+ | -- | Cost/Duration = 2.1/15 = $0.14M/year
Discussion | Installation of these cap banks provide a valid solution through 2023. E Helena and Three Rivers subs well developed and should accommodate cap banks, but new sub may be required at Broadwater or close vicinity. Solution could be staged in over time.