## CROW - Outage Request Listing
CROW - Outage Request Listing
2017/01/13 13:08
Outage #/Revision/Status | Station/Circuit/Equipment/Path Description | Outage Start | Outage Complete | Required Approvals | Comments
1-00415646 Revision #3 Submitted | O'Brien - Long Lake 115 kV Line : Robinson Pt. Cable Sta. - Vashon OOS | 2016/10/17 06:00 | 2017/01/31 15:00 | PSE-TCC: Pending | Grieger, Lisa
1-00434005 Revision #4 Cancelled | Lakeside - Phantom Lake 115 kV Line : College - Phantom Lake COL SW #1285 to PHA HS SW #469 OOS | 2017/01/03 07:00 | 2017/01/07 19:00 | CISO-TCC: n/a PSE-TCC: n/a | McCulloch, Al J. Cell Site Work
1-00428214 Revision #2 Submitted | BPA Snohomish - Beverly Park #4 115 kV Line : BPA Snohomish - Beverly Park BEV PCB 471-L Terminal Clearance OOS | 2017/01/03 07:00 | 2017/01/26 17:30 | CISO-TCC: Pending PSE-TCC: Pending | McCulloch, Al J. BPA Replacing CT's and Rod Gaps
1-00428177 Revision #12 Submitted | Snohomish-Beverly Park 4 115kV Line, Snohomish: PCB B-486 OOS | 2017/01/03 09:38 | 2017/01/26 16:30 | BPA-TCC: Pending PSE-TCC: Pending SNPD-TCC: Pending | BPA, Dart #1084579 REPLACE METERING CT'S & ROD GAPS
1-00438308 Revision #1 Submitted | Shuffleton - President Park 115 kV Line : Shuffleton - Highlands, Shuffleton 115kV 1309_A, Shuffleton 115kV 1309_M OOS | 2017/01/05 07:00 | 2017/01/05 18:00 | PSE-TCC: Pending CISO-TCC: Pending | Morse, Kenneth Repair PCB 1309 line disconnects
1-00438258 Revision #1 Submitted | White River - Alpac 115 kV Line : Dieringer Tap - Alpac, Alpac 115kV P130 OOS | 2017/01/05 09:00 | 2017/01/05 14:00 | PSE-TCC: Pending CISO-TCC: Pending | Morse, Kenneth Changes to PCB 130 re closing circuit
1-00434442 Revision #8 Submitted | Sedro Woolley - Bellingham #3 115 kV Line : Woburn - Bellingham BHM PCB 466-L to WOD SW #746 OOS | 2017/01/06 05:00 | 2017/01/06 18:00 | CISO-TCC: Pending PSE-TCC: Pending | McCulloch, Al J. Proximity Steel Work at Bellingham Svc. Ctr.
1-00440975 Revision #2 Submitted | Berrydale - Krain Corner 115 kV Line : Pipe Lake - Four Corners OOS | 2017/01/08 11:26 | 2017/01/08 21:00 | CISO-TCC: Pending PSE-TCC: Pending | Morse, Kenneth Tree in line
1-00440982 Revision #2 Submitted | CF-LY 115kV Line OOS | 2017/01/08 11:47 | 2017/01/09 00:10 | PSE-TCC: Pending SCL-TCC: Pending | Dissel, Christopher Forced out. Tripped offline
1-00441092 Revision #2 Submitted | South Bremerton - Long Lake #2 115 kV Line : Sinclair Inlet - Fernwood Tap OOS | 2017/01/09 06:29 | 2017/01/09 19:35 | CISO-TCC: Pending PSE-TCC: Pending | Shore, Daniel Car pole accident
1-00441147 Revision #4 Submitted | Snohomish-Beverly Park 4 115kV Line, Snohomish: PCB B-486 OOS | 2017/01/09 09:16 | 2017/02/01 16:30 | BPA-TCC: Pending PSE-TCC: Pending SNPD-TCC: Pending | BPA, Dart #1093933 REPLACE METERING CT'S & ROD GAPS
1-00441372 Revision #1 Submitted | Christopher Tap to Tacoma-Covington 2 230kV Line OOS | 2017/01/10 02:15 | 2017/01/10 02:22 | BPA-TCC: Pending PSE-TCC: Pending | BPA, Dart
1-00441704 Revision #2 Submitted | O'Brien 115kV P942_L, O'Brien 115kV P942_M, Obrien P942 OOS | 2017/01/10 18:44 | 2017/01/11 16:00 | PSE-TCC: Pending CISO-TCC: Pending | Morse, Kenneth Breaker fail PCB 942
1-00436637 Revision #1 Submitted | Sammamish - Lochleven 115 kV Line : Overlake Loop (42437) - Lochleven OOS | 2017/01/11 08:00 | 2017/01/11 15:00 | PSE-TCC: Pending CISO-TCC: Pending | McCulloch, Al J. Remove down guys on pole SW #234
1-00442442 Revision #1 Submitted | O'Brien - Long Lake 115 kV Line : Midway - S. Des Moines Cable Sta., O'Brien - Long Lake 115 kV Line : O'Brien - Midway OOS | 2017/01/13 11:00 | 2017/01/13 18:00 | PSE-TCC: Pending CISO-TCC: Pending | Bishop, Warren
1-00440194 Revision #1 Submitted | Whidbey - Greenbank #1 115 kV Line : Whidbey - Coupeville OOS | 2017/01/17 08:00 | 2017/01/17 16:00 | PSE-TCC: Pending CISO-TCC: Pending | McCulloch, Al J. Replace armour rod and trunnion clamps
1-00438198 Revision #1 Submitted | White River - O'Brien #2 115 kV Line : West Auburn - O'Brien OOS | 2017/01/19 08:30 | 2017/01/20 18:00 | PSE-TCC: Pending CISO-TCC: Pending | McCulloch, Al J. Proximity work, setting distribution pole.
1-00441356 Revision #1 Submitted | Electron Heights - Yelm 115 kV Line : Kapowsin - Yelm OOS | 2017/01/23 06:30 | 2017/01/23 16:00 | PSE-TCC: Pending CISO-TCC: Pending | McCulloch, Al J. Emergency Pole Replacement
1-00441656 Revision #2 Submitted | Lakeside - Phantom Lake 115 kV Line : College - Phantom Lake, Lakeside - Phantom Lake 115 kV Line : Lakeside - College, College 115kV SW1124 OOS | 2017/01/23 08:00 | 2017/02/03 19:00 | CISO-TCC: Pending PSE-TCC: Pending | McCulloch, Al J. Cell site work and replacement of COL SW #1285
1-00439847 Revision #2 Submitted | Christopher Tap to Tacoma-Covington 2 230kV Line, Christopher-Covington Section of Tacoma-Covington 2 230kV Line, Tacoma-Christopher Section of Tacoma-Covington 2 230kV Line, Tacoma-Covington 2 230kV Line OOS | 2017/02/15 16:00 | 2017/02/28 16:30 | BPA-TCC: Pending PSE-TCC: Pending | BPA, Dart #1092761 LINE DEENERGIZED TO ALLOW SWITCHING AT CHRISTOPHER TAP SWITCH 973
1-00442085 Revision #2 Submitted | Terrell - Refinery 115 kV Line : Terrell - Refinery TER PCB 3261-D1 to TER PCB 3262-D2 to WPR PCB 5507-D5524 to WPR PCB-D5519, Ferndale CT1, Ferndale CT2 OOS | 2017/02/28 06:30 | 2017/02/28 17:00 | CISO-TCC: Pending PSE-TCC: Pending CISO-GCC: Pending PSE-GCC: Pending | McCulloch, Al J. NERC end to end testing of scheme 57 and related relay and communication testing.
1-00442171 Revision #2 Submitted | Sammamish - BPA Maple Valley #1 230 kV Line : Klahanie - Novelty OOS | 2017/02/28 08:00 | 2017/02/28 22:30 | PSE-TCC: Pending CISO-TCC: Pending | McCulloch, Al J. Replace motor operator on KLA SW #1315. This is a 45 day line.