## CROW Web - Outage Request Listi
CROW Web - Outage Request Listing
2017/04/06 18:57
Outage #/Revision/Status | Station/Circuit/Equipment/Path Description | Outage Start | Outage Complete | Required Approvals | Requested By/Comments
1-00446753 Revision #5 TOP Confirmed | South Bremerton - Valley Junction 115 kV Line : Tracyton - Valley Junction OOS | 2017/03/20 05:00 | 2017/04/07 18:00 |  | Morse, Kenneth Raising line 20 ft/installing 4 poles
1-00458807 Revision #9 TOP Confirmed | Greenbank 115kV 3234_L, Greenbank 115kV 3234_M, Greenbank 115kV CB 3234 OOS | 2017/03/27 07:00 | 2017/04/07 17:00 |  | McCulloch, Al J. Relay Package upgrade
1-00448486 Revision #2 Cancelled | White River - O'Brien #2 115 kV Line : West Auburn - O'Brien, Obrien P70, West Auburn 115kV SW1005 OOS | 2017/03/30 08:00 | 2017/04/12 16:00 |  | Thrasher, John Safet watch outage while stringing wire over conductors
1-00439524 Revision #4 Cancelled | Christopher - O'Brien #4 230 kV Line : O'Brien - BPA Covington/Tacoma, Christopher Tap to Tacoma-Covington 2 230kV Line, Christopher 230kV SW973 OOS | 2017/03/30 08:00 | 2017/04/12 16:00 | BPA-TCC: n/a CISO-TCC: n/a PSE-TCC: n/a | Thrasher, John Setting two steel poles and transferring wires straddling South 228th Street
1-00463718 Revision #4 TOP Confirmed | Anderson Canyon - Beverly Park 115kV OOS | 2017/03/31 08:00 | 2017/04/14 16:00 |  | Bishop, Warren Inspecting cross arms.
1-00461220 Revision #2 Cancelled | Talbot Hill - Berrydale #1 115 kV Line : Panther Lake Tap - Glencarin OOS | 2017/04/01 07:00 | 2017/04/01 19:00 |  | McCulloch, Al J. Cell Site
1-00453391 Revision #2 Submitted | Blumaer - Saint Clair 115 kV Line : Blumaer - Saint Clair OOS | 2017/04/01 08:00 | 2017/04/04 16:00 | CISO-TCC: Pending PSE-TCC: Pending | Grieger, Lisa apply new relay settings
1-00461418 Revision #1 Submitted | Whitehorn 115kV P496, Whitehorn 115kV P496_M, Whitehorn Unit 2 OOS | 2017/04/03 06:00 | 2017/04/28 16:00 | PSE-TCC: Pending CISO-TCC: Pending PSE-GCC: Pending | McCulloch, Al J. Annual Maintenance & Starting Package refurbishment.
1-00462591 Revision #1 Submitted | Foss Corner - Port Madison 115 kV Line : Foss Corner - Kingston Tap OOS | 2017/04/03 07:00 | 2017/04/03 15:30 |  | Kauer, Kaysee remove abandoned transformer and regulator from station
1-00461209 Revision #2 Submitted | Sammamish - Moorlands #1 115 kV Line : Inglewood - Juanita OOS | 2017/04/03 07:00 | 2017/04/10 19:00 |  | McCulloch, Al J. Cell Site
1-00462292 Revision #9 Implemented Unverified | Christopher - O'Brien #4 230 kV Line : O'Brien - BPA Covington/Tacoma, White River - O'Brien #2 115 kV Line : West Auburn - O'Brien OOS | 2017/04/03 07:30 | 2017/04/21 17:00 |  | Parker, David Setting 2 steel poles and transferring conductor. White River - O'Brien #2 is in close proximity for crane work on Christopher - O'Brien #4 rescheduled from COS# 1-00439524
1-00463519 Revision #1 Submitted | Christopher - O'Brien #4 230 kV Line : O'Brien - BPA Covington/Tacoma, White River - O'Brien #2 115 kV Line : West Auburn - O'Brien OOS | 2017/04/03 07:30 | 2017/04/21 17:00 |  | Yoon, Chris Duplicate of COS ID: 462292
1-00439863 Revision #16 Completed Unverified | Tacoma-Covington 2 230kV Line OOS | 2017/04/03 07:30 | 2017/04/03 08:00 |  | BPA, Dart #1092765 LINE DEENERGIZED FOR PSE SWITCHING AT CHRISTOPHER TAP SWITCH 973
1-00464338 Revision #1 Completed Verified | O'Brien - Long Lake 115 kV Line : Command Pt. Cable Sta. - Fragaria Tap, O'Brien - Long Lake 115 kV Line : Cove Cable Sta. - Command Pt. Cable Sta., O'Brien - Long Lake 115 kV Line : Vashon - Cove Cable Sta. OOS | 2017/04/03 08:37 | 2017/04/03 16:00 |  | Harris, Andrew Line tripped, unknown cause at this time.
1-00461802 Revision #1 Submitted | Berrydale - Lake Tradition #1 115 kV Line : Mirrormont - Lake Tradition OOS | 2017/04/03 18:00 | 2017/05/05 06:00 | PSE-TCC: Pending CISO-TCC: Pending | McCulloch, Al J.
1-00463175 Revision #2 Submitted | Lakeside - Lochleven 115 kV Line : Lakeside - South Bellevue, Sammamish - Lakeside #2 115 kV Line : Rosehill Tap - Lakeside OOS | 2017/04/04 07:00 | 2017/04/05 16:00 |  | Kauer, Kaysee Proximity work, boring crew preparing for next week's outage replacing H structure.
1-00441304 Revision #3 Submitted | Sedro Woolley - Horse Ranch 230 kV Line : Sedro Woolley - Horse Ranch OOS | 2017/04/04 08:00 | 2017/04/04 16:00 |  | McCulloch, Al J. NERC Trip Checks for Scheme 115 Per BPA: New TTC for SOC and NOEL during Sedro Woolley-Horse Ranch outage SOC = 3132 MW NOEL = 2746 MW
1-00449219 Revision #30 TOP Confirmed | Paul-PSE Tono 1 500kV Line, Paul: 500kV North Bus, Paul: PCB 4536, Paul: PCB 4544, Paul: PCB 4554, Paul: PCB 4804, Paul: PCB 4818 OOS | 2017/04/05 07:30 | 2017/04/07 16:00 |  | BPA, Dart #1089891 COMPLETE SERVICE ON MOD 4805/REACTOR 1 WORK./SET LIMIT SWITCHES ON NEW MODS, TRIP CHECKS, AND IN SERVICE CHECKS //ttc = 1800 MW Monitoring Element = Chehalis-Covington 230kV Line Contingent Element = Raver-Paul 1 500kV Line Violation Type = Facility Rating Refer to DSO 307 for operating procedures: Per BPA’s internal policy, if actual flows on the Path exceed the MAX ALIS TTC, these flows shall be reduced below the limit within 30 minutes or less. section III.C.5. "MAX ALIS TTC Exceeded" section III.C.6. "Raver-Paul Facility Rating SOL Exceeded"
1-00460105 Revision #1 Submitted | BPA Paul - Tono #1 500kV Line : BPA Paul - Tono OOS | 2017/04/05 07:30 | 2017/04/07 16:00 | BPA-TCC: Pending PSE-TCC: Pending | McCulloch, Al J. BPA performaing maintenance on PCB 4804 disconnect 4805
1-00457750 Revision #1 Submitted | Sedro Woolley - March Point #3 115 kV Line : Blackburn - Hickox Tap OOS | 2017/04/05 09:00 | 2017/04/05 11:00 | PSE-TCC: Pending CISO-TCC: Pending | Kauer, Kaysee Breaker profiling
1-00463153 Revision #3 Submitted | Sammamish - Lakeside #1 115 kV Line : Rosehill - Lakeside OOS | 2017/04/06 07:00 | 2017/04/07 17:00 |  | Kauer, Kaysee Proximity work, boring work preparing for replacing H structures
1-00458802 Revision #6 RC OPA D+2 Confirmed | Greenbank 115kV 3235, Greenbank 115kV 3235_L, Greenbank 115kV 3235_M OOS | 2017/04/10 07:00 | 2017/04/12 17:00 |  | McCulloch, Al J. GBK 3235 Major Maintenace
1-00457017 Revision #6 RC OPA D+2 Confirmed | Whidbey - Greenbank #1 115 kV Line : Whidbey - Coupeville OOS | 2017/04/10 07:00 | 2017/04/14 17:00 |  | McCulloch, Al J. Replace two poles
1-00463738 Revision #6 RC OPA D+2 Confirmed | Christopher - Starwood 115 kV Line : Marine View - Weyerhauser Tap OOS | 2017/04/10 07:00 | 2017/04/12 18:00 |  | Bishop, Warren
1-00463747 Revision #5 RC OPA D+2 Confirmed | Talbot Hill - Berrydale #1 115 kV Line : Panther Lake Tap - Glencarin OOS | 2017/04/10 07:00 | 2017/04/15 18:00 |  | Bishop, Warren
1-00462240 Revision #6 RC Short-Range Confirmed | Sammamish - Lakeside #1 115 kV Line : Rosehill - Lakeside, Sammamish - Lakeside #1 115 kV Line : Sammamish - Rosehill OOS | 2017/04/11 07:00 | 2017/04/12 18:00 |  | Parker, David Replacing H-Structure
1-00460683 Revision #5 RC Short-Range Confirmed | South Whidbey - Greenbank #1 115 kV Line : Greenbank - Freeland Tap Major Maint on GBK 3235 OOS | 2017/04/11 07:00 | 2017/04/12 17:00 |  | Weboms, CAISO Major Maint on GBK 3235
1-00441216 Revision #9 RC Short-Range Confirmed | Terrell - Arco South 115 kV Line : Terrell - Olympic Arco Pump Tap OOS | 2017/04/11 08:00 | 2017/04/11 16:00 |  | McCulloch, Al J. NERC End to End Trip Testing. One Terrell PCB will always be closed energizing the line for Olympic Avon.
1-00451941 Revision #2 Cancelled | Paul-PSE Tono 1 500kV Line, Paul: PCB 4804 OOS | 2017/04/12 07:30 | 2017/04/12 14:30 | BPA-TCC: n/a PSE-TCC: n/a | BPA, Dart #1095395 COMPLETE SERVICE ON MOD 4805
1-00463784 Revision #6 RC Short-Range Confirmed | Stillwater - Cottage Brook 115 kV Line : Duvall Tap - Stillwater OOS | 2017/04/13 08:00 | 2017/05/09 16:00 |  | Bishop, Warren
1-00462242 Revision #5 RC Short-Range Confirmed | Lakeside - Lochleven 115 kV Line : Lakeside - South Bellevue, Sammamish - Lakeside #2 115 kV Line : Rosehill Tap - Lakeside, Sammamish - Lakeside #2 115 kV Line : Sammamish - Rosehill Tap OOS | 2017/04/13 08:00 | 2017/04/14 16:00 |  | Parker, David Long-Line E Replacing H-Structure
1-00451506 Revision #3 Cancelled | Monroe-Horse Ranch Section of Monroe-Snohomish 1&2 230kV Line, Monroe-Novelty Hill 1 230kV Line, Monroe: 230kV Main Bus, Monroe: 500/230kV Bank 1 OOS | 2017/04/17 07:00 | 2017/04/17 15:30 |  | BPA, Dart #1079899 ROUTINE MAINTENANCE, IN SERVICE AND TRIP CHECKS
1-00463744 Revision #2 TOP Confirmed | Lakeside - Mercer Island 115 kV Line : Mercer Island Tap - Mercerwood Tap OOS | 2017/04/17 07:00 | 2017/04/17 18:00 |  | Bishop, Warren
1-00441347 Revision #6 TOP Confirmed | Sedro Woolley - SCL Bothell 230 kV Line : Horse Ranch Tap - SCL Bothell, Sedro Woolley - SCL Bothell 230 kV Line : Sedro Woolley - Horse Ranch Tap OOS | 2017/04/17 08:00 | 2017/04/17 16:00 |  | McCulloch, Al J. NERC Trip Checks for Scheme 18 45 day outage notification line.
1-00439043 Revision #5 TOP Confirmed | Anderson Canyon - Beverly Park 115kV OOS | 2017/04/18 07:00 | 2017/04/21 15:00 |  | TOA, Chelan 379809 CC-SM 17/4 replace type A. Rescheduled due to Puget's emergency outage between Beverly Park and Skykomish
1-00464379 Revision #2 TOP Confirmed | Sedro Woolley - March Point #2 115 kV Line : Anacortes Pump Tap - March Point OOS | 2017/04/18 07:00 | 2017/04/18 17:00 |  | McCulloch, Al J. Setting new distribution pole
1-00463311 Revision #2 TOP Confirmed | Talbot Hill P657 trip checks Op. Restr.: Operating Restriction | 2017/04/18 09:00 | 2017/04/18 09:30 |  | Weboms, CAISO trip checks
1-00457752 Revision #2 TOP Confirmed | Sedro Woolley 115kV 881, Sedro Woolley 230kV 3156, Sedro Woolley 230kV 7478, Sedro Woolley 230kV 7539 OOS | 2017/04/19 09:00 | 2017/04/19 13:00 |  | Kauer, Kaysee breaker profiling. One breaker at a time. Open and close less than 30 minutes out of service.
1-00466113 Revision #2 TOP Confirmed | Talbot Hill - Boeing Renton #2 115 kV Line : Paccar - Boeing Renton #2 OOS | 2017/04/20 06:00 | 2017/04/20 18:00 |  | Parker, David Removing tap from Shuffleton PCB 910 to TAL-BRT
1-00439870 Revision #9 TOP Confirmed | Christopher-Covington Section of Tacoma-Covington 2 230kV Line, Tacoma-Christopher Section of Tacoma-Covington 2 230kV Line, Tacoma-Covington 2 230kV Line OOS | 2017/04/21 16:00 | 2017/04/21 16:30 |  | BPA, Dart #1092767 LINE DEENERGIZED TO ALLOW PSE SWITCHING AT CHRISTOPHER TAP SWITCH 973
1-00461445 Revision #1 Submitted | BPA Bellingham - Lynden 115 kV Line: Lynden - Hannegan, Lynden 115kV P3013_L, Lynden 115kV SW3013, Lynden 115kV SW3122, Lynden 115kV SW3216 OOS | 2017/04/24 07:00 | 2017/04/28 16:00 | PSE-TCC: Pending CISO-TCC: Pending | McCulloch, Al J. Replacing LYN SW #3043
1-00464788 Revision #1 TOP Proposed | O'Brien - Asbury 115 kV Line : O'Brien - Harvest, O'Brien - Christopher #2 115 kV Line : Kent - O'Brien, O'Brien - Metro Renton 115 kV Line : O'Brien - Orillia, O'Brien - Midway #2 115 kV Line : O'Brien - Manhattan, Shuffleton - O'Brien 115 kV Line : Falcon - O'Brien, Obrien 230/115kv Bank 1 OOS | 2017/04/24 09:00 | 2017/04/24 09:30 |  | Parker, David O'Brien north bus lockout relay trip test
1-00464780 Revision #1 TOP Proposed | Shuffleton - President Park 115 kV Line : Shuffleton - Highlands OOS | 2017/04/25 09:00 | 2017/04/25 13:00 |  | Parker, David Shuffleton east bus lock out relay trip checks
1-00464775 Revision #3 TOP Proposed | Shuffleton - Boeing Renton #1 115 kV Line : Shuffleton - Boeing Renton #1, Shuffleton - O'Brien 115 kV Line : Shuffleton - Earlington OOS | 2017/04/26 09:00 | 2017/04/26 13:00 |  | Parker, David Shuffleton west bus lockout relay trip checks
1-00461703 Revision #2 TOP Proposed | BPA Maple Valley - Talbot Hill #2 230 kV Line : BPA Maple Valley - Talbot Hill, Talbot Hill - O'Brien #3 230 kV Line : Talbot Hill - O'Brien, Talbot Hill - SCL South 230kV Line : Talbot Hill - SCL South OOS | 2017/04/27 04:00 | 2017/04/27 04:10 |  | McCulloch, Al J. To Cut In TAL SW #724 on a dead bus.
1-00461339 Revision #3 TOP Proposed | BPA Maple Valley - Talbot Hill #2 230 kV Line : BPA Maple Valley - Talbot Hill OOS | 2017/04/27 04:00 | 2017/04/28 04:10 |  | McCulloch, Al J. BPA work on A1130
1-00461340 Revision #3 TOP Proposed | BPA Maple Valley - Talbot Hill #2 230 kV Line : BPA Maple Valley - Talbot Hill, Talbot Hill - O'Brien #3 230 kV Line : Talbot Hill - O'Brien, Talbot Hill - SCL South 230kV Line : Talbot Hill - SCL South OOS | 2017/04/27 04:00 | 2017/04/27 04:10 |  | McCulloch, Al J. Momentary outage to switch out TAL SW #724 for BPA work.
1-00432594 Revision #4 Submitted | Talbot Hill - O'Brien #2 115 kV Line : Talbot Hill - Victoria Park TAL PCB-L&A to VIC SW# 1022 OOS | 2017/04/27 06:00 | 2017/05/12 16:00 | CISO-TCC: Pending PSE-TCC: Pending | McCulloch, Al J. Proximity work for sound walls.
1-00396222 Revision #11 TOP Proposed | Maple Valley-Talbot 2 230kV Line, Maple Valley: PCB A-1130 OOS | 2017/04/27 08:00 | 2017/04/28 04:30 |  | BPA, Dart #1053029 A-1130 LINE AND A/B DISCONNECTS COMPLETE & CORRECTIVE SERVICES //soc max ttc = 3700 mw monitored element contingent element violation type portalway 230/115kv bank bellingham-custer 1 230kv line and murray-custer 1 230kv line facility rating murray-sedro 230kv line monroe-custer 1&2 500kv lines facility rating monroe 500/230kv bank bfr 5111 echo Lake-monroe-snoking 1 500kv line and echo lake 500kv capacitor facility rating OPERATING PLAN : PRE-CTG REFER TO DSO 349 FOR OPERATING PROCEDURES: SECTION IV. D. "RESPONSE TO ALARM MESSAGES" ATTACHMENT 5 OPERATING PLAN: POST-CTG REFER TO DSO 349 FOR OPERATING PROCEDURES: PER BPA'S INTERNAL POLICY, IF ACTUAL FLOWS ON THE PATH EXCEED THE MAX ALIS TTC, THESE FLOWS SHALL BE REDUCED BELOW THE LIMIT WITHIN 30 MINUTES OR LESS FOR ALIS AND OUTAGE CONDITIONS. SECTION IV. D. "RESPONSE TO ALARM MESSAGES" ATTACHMENT 5 NOEL max TTC = 2746 MONITORED ELEMENT contingent element violation type MONROE-CUSTER #2 500KV LINE BFR 4268 MONROE-CUSTER #1 500KV LINE AND CUSTER 500/230KV BK 1 facility rating BROAD ST-UNION #1 115KV LINE BFR 4526 MONROE-ECHO LAKE-SNOKING #1 500KV LINE AND MONROE-CUSTER #1 500KV LINE facility rating PORTALWAY 230/115KV BK BELLINGHAM-CUSTER #1 230KV LINE AND MURRAY-CUSTER #1 230KV LINE facility rating OPERATING PLAN: PRE-CTG REFER TO DSO 348 FOR OPERATING PROCEDURES: SECTION IV. D. "RESPONSE TO ALARM MESSAGES" ATTACHMENT 5 OPERATING PLAN: POST-CTG REFER TO DSO 348 FOR OPERATING PROCEDURES: PER BPA'S INTERNAL POLICY, IF ACTUAL FLOWS ON THE PATH EXCEED THE MAX ALIS TTC, THESE FLOWS SHALL BE REDUCED BELOW THE LIMIT WITHIN 30 MINUTES OR LESS FOR ALIS AND OUTAGE CONDITIONS. SECTION IV. D. "RESPONSE TO ALARM MESSAGES" ATTACHMENT 5
1-00432356 Revision #3 Submitted | BPA Maple Valley - Talbot Hill #2 230 kV Line : BPA Maple Valley - Talbot Hill, Talbot Hill - O'Brien #3 230 kV Line : Talbot Hill - O'Brien, Talbot Hill - SCL South 230kV Line : Talbot Hill - SCL South, Talbot Hill 230/115kv Bank 2, Talbot Hill 230kV SW685 OOS | 2017/04/27 08:00 | 2017/10/31 16:00 | CISO-TCC: Pending PSE-TCC: Pending | Grieger, Lisa Terminal clearance needed: BMA A-1130 and SCL SOS PCB 240-9. Rebuild Talbot Hill 230kv north bus.
1-00443882 Revision #3 Submitted | BPA Maple Valley - Talbot Hill #1 230 kV Line : BPA Maple Valley - Talbot Hill, BPA Maple Valley - Talbot Hill #2 230 kV Line : BPA Maple Valley - Talbot Hill, Talbot Hill - Berrydale #3 230 kV Line : Talbot Hill - Berrydale, Talbot Hill 230kV SW650, Talbot Hill 230kV SW724 OOS | 2017/04/27 08:00 | 2017/04/27 17:00 | CISO-TCC: Pending PSE-TCC: Pending | Kauer, Kaysee Talbot South Bus outage to remove Bus section switch 685. Will need a terminal Clearance from BPA on BMA PCB A1120 and A1130 line side disconnects.
1-00443930 Revision #2 Submitted | Talbot Hill - Berrydale #1 115 kV Line : Talbot Hill - Rolling Hills, Talbot Hill - Lake Tradition #1 115 kV Line : Maplewood - Lake Tradition, Talbot Hill - Lakeside #1 115 kV Line : Talbot Hill - Lakeside, Talbot Hill - Metro Renton 115 kV Line : Metro Renton - Grady, Talbot Hill - O'Brien #2 115 kV Line : Talbot Hill - Victoria Park, Talbot Hill 115kV P653_M, Talbot Hill 115kV P654_BK2 OOS | 2017/04/27 08:00 | 2017/04/27 18:00 | CISO-TCC: Pending PSE-TCC: Pending | Kauer, Kaysee Removing lines over Bank # 2
1-00443324 Revision #1 Submitted | March Point 230/115kv Bank OOS | 2017/05/02 07:00 | 2017/05/02 17:00 | PSE-TCC: Pending CISO-TCC: Pending | McCulloch, Al J. Relay Trip Checks and relay testing
1-00463765 Revision #2 TOP Proposed | Cottage Brook - Moorlands 115 kV Line : Cottage Brook - Hollywood OOS | 2017/05/08 06:00 | 2017/05/09 16:00 |  | Bishop, Warren
1-00461046 Revision #5 TOP Proposed | Sammamish - Moorlands #1 115 kV Line : Crestwood Tap - Norkirk, Sammamish - Moorlands #1 115 kV Line : Juanita - Crestwood Tap OOS | 2017/05/11 06:00 | 2017/05/11 18:00 |  | McCulloch, Al J. Pole SW #1052 Maintenance
1-00456908 Revision #7 TOP Proposed | Beverly Park - Cottage Brook 115 kV Line : Lake Leota - Cottage Brook, Cottage Brook - Moorlands 115 kV Line : Cottage Brook - Hollywood, Sammamish - Novelty Hill - Cottage Brook 115 kV Line : Avondale - Cottage Brook, Stillwater - Cottage Brook 115 kV Line : Cottage Brook - Duvall Tap, Cottage Brook Cottage Brook OOS | 2017/05/11 06:00 | 2017/05/12 17:00 |  | McCulloch, Al J. Replacing COT PCB 1003-M Disconnects
1-00457004 Revision #5 TOP Proposed | Novelty Hill - Stillwater 115 kV Line : Novelty Hill - Stillwater, Snoqualmie - Novelty Hill 115 kV Line : Novelty Hill - Tolt Tap OOS | 2017/05/12 05:00 | 2017/05/13 16:00 |  | McCulloch, Al J. Replacing NOV PCB 1301 Main Bus Disconnects. NOTE: The entire Novelty 115kV bus will be de-energized, temporarily to facilitate switching. An RTCA study will be done before switching.
1-00454687 Revision #3 Submitted | Talbot Hill - Christopher 115 kV Line : Orchard - Talbot OOS | 2017/05/13 07:00 | 2017/05/24 16:00 | CISO-TCC: Pending PSE-TCC: Pending | McCulloch, Al J. Proximity Work for I405 State work.
1-00443077 Revision #4 TOP Proposed | Mullan-Central Ferry 230KV Line, Phalen Gulch-Central Ferry 230kV Line, Central Ferry: 500/230kV Bank 1 OOS | 2017/05/15 08:00 | 2017/05/19 17:00 |  | BPA, Dart #1094553 DIAGNOSTIC SERVICE.
1-00464820 Revision #1 TOP Proposed | Stillwater - Cottage Brook 115 kV Line : Cottage Brook - Duvall Tap, Stillwater - Cottage Brook 115 kV Line : Duvall Tap - Stillwater OOS | 2017/05/18 07:30 | 2017/05/26 16:00 |  | Parker, David replacing poles
1-00460324 Revision #4 TOP Proposed | Mullan-Central Ferry 230KV Line, Phalen Gulch-Central Ferry 230kV Line, Central Ferry: 500/230kV Bank 1, Central Ferry: PCB 5388, Central Ferry: PCB 5391, Central Ferry: PCB A-1762, Central Ferry: PCB A-1766, Central Ferry: PCB A-1780 OOS | 2017/05/18 08:00 | 2017/05/18 16:00 |  | BPA, Dart #1097261 TRIP CHECKS TO PCB(S) 5388, 5391, A-1762, A-1766, AND A-1780.
1-00456247 Revision #6 Submitted | Portal Way - Arco Central 115 kV Line : Portal Way - Arco Central OOS | 2017/05/22 07:00 | 2017/06/02 17:00 |  | Bishop, Warren Pole replacement and relocate transmission lines
1-00463315 Revision #1 TOP Proposed | Talbot Hill - Lakeside #1 115 kV Line : Talbot Hill - Lakeside OOS | 2017/05/23 09:00 | 2017/05/23 14:00 |  | Kauer, Kaysee Relay tests and trip checks.
1-00464824 Revision #1 TOP Proposed | Stillwater - Cottage Brook 115 kV Line : Cottage Brook - Duvall Tap OOS | 2017/05/26 16:00 | 2017/10/06 16:00 |  | Parker, David replacing poles and re-conductoring line
1-00461401 Revision #3 TOP Proposed | Sedro Woolley-Bellingham 1 230kV Line OOS | 2017/05/30 07:00 | 2017/05/30 16:30 |  | BPA, Dart #1098749 CT DIAGNOSTIC SERVICE
1-00461475 Revision #1 Submitted | Sedro Woolley-Bellingham 1 230kV Line OOS | 2017/05/30 07:00 | 2017/05/30 16:30 | BPA-TCC: Pending PSE-TCC: Pending | McCulloch, Al J. BPA work on BBE A312 CT's
1-00457718 Revision #1 Submitted | South Bremerton 230kV 7124_L, South Bremerton 230kV 7124_M OOS | 2017/05/30 08:00 | 2017/06/01 16:30 | PSE-TCC: Pending CISO-TCC: Pending | Kauer, Kaysee MECHANISM MAINTENANCE AND TESTING
1-00466610 Revision #1 TOP Confirmed | Bellingham: Whatcom CO PUD 115kV Feeder 1, Bellingham: PCB B-936 OOS | 2017/05/31 07:00 | 2017/05/31 16:00 |  | BPA, Dart #1098773 CT DIAGNOSTIC SERVICE
1-00442410 Revision #2 Submitted | Sedro Woolley - March Point 230 kV Line : Fredonia Tap - Sedro Woolley, Sedro Woolley - March Point 230 kV Line : March Point - Fredonia Tap OOS | 2017/06/05 07:00 | 2017/06/05 16:00 | CISO-TCC: Pending PSE-TCC: Pending | Kauer, Kaysee Replacing 230kv disconnect switches
1-00454698 Revision #2 Submitted | Talbot Hill - Christopher 115 kV Line : Orchard - Talbot OOS | 2017/06/05 07:00 | 2017/06/19 16:00 | CISO-TCC: Pending PSE-TCC: Pending | McCulloch, Al J. Proximity work by I405 State Contractor
1-00452056 Revision #4 Submitted | Sedro Woolley - March Point 230 kV Line : Fredonia Tap - Sedro Woolley, Sedro Woolley - March Point 230 kV Line : March Point - Fredonia Tap OOS | 2017/06/06 08:00 | 2017/06/16 16:00 | CISO-TCC: Pending PSE-TCC: Pending | Harris, Andrew Replace 7 rotten poles, returned nightly & weekends
1-00443371 Revision #1 Submitted | Sedro 230/115kv Bank 1, Sedro Woolley 115kV 676, Sedro Woolley 115kV 676_A, Sedro Woolley 115kV 676_M, Sedro Woolley 230kV 3159, Sedro Woolley 230kV 3159_D2, Sedro Woolley 230kV 735, Sedro Woolley 230kV 735_D1 OOS | 2017/06/14 07:00 | 2017/06/14 16:00 | PSE-TCC: Pending CISO-TCC: Pending | McCulloch, Al J. Relay testing and trip checks
1-00462832 Revision #2 TOP Proposed | Diablo - Bothell #1 230kV Line Diabo Substation to Bothell Substation #1 230kv Line, SCL Bothell - Sammamish 230 kV Line : SCL Bothell - Sammamish Bothell Substation to Sammamish Substation 230kv Line, SCL Bothell Bank #62 Bothell Substation Bank 62, SCL Bothell PCB 240-66 Bothell Substation Bkr 240-66, SCL Bothell PCB 240-69 Bothell Substation Bkr 240-69 OOS | 2017/07/20 08:00 | 2017/07/21 20:00 |  | Sandoval, Marcus Bkr 240-66 Relay Testing after Replacement
1-00443146 Revision #1 Submitted | White River - Alderton #4 115 kV Line : Stewart Tap - Alderton Cut Jumpers at grid 568093/156133 to ALD 1283-L&A OOS | 2017/08/01 08:00 | 2017/10/31 16:00 | PSE-TCC: Pending CISO-TCC: Pending | Bishop, Warren
1-00443148 Revision #1 Submitted | White River - Alderton #4 115 kV Line : Stewart Tap - Alderton OOS | 2017/08/01 08:00 | 2017/08/01 16:00 | PSE-TCC: Pending CISO-TCC: Pending | Bishop, Warren
1-00443150 Revision #1 Submitted | White River - Fairchild 115 kV Line : Woodland - Fruitland OOS | 2017/08/01 09:00 | 2017/08/01 16:00 | CISO-TCC: Pending PSE-TCC: Pending | Bishop, Warren
1-00456256 Revision #2 TOP Proposed | Olympia-Shelton 5 230kV Line, Olympia-St Clair 1 230KV Line, Olympia: 230kV Center Main Bus, Olympia: PCB A-1770, Olympia: PCB A-206, Olympia: PCB A-356, Olympia: PCB A-358 OOS | 2017/08/22 07:30 | 2017/08/22 16:30 |  | BPA, Dart #1095665 DISCONNECT MAINTENANCE
1-00454702 Revision #2 Submitted | Talbot Hill - Christopher 115 kV Line : Orchard - Talbot OOS | 2017/08/27 07:00 | 2017/09/03 16:00 | CISO-TCC: Pending PSE-TCC: Pending | McCulloch, Al J. Proximity work at I405 with state contractor
1-00443152 Revision #1 Submitted | White River - Fairchild 115 kV Line : Woodland - Fruitland OOS | 2017/10/31 08:00 | 2017/10/31 16:00 | CISO-TCC: Pending PSE-TCC: Pending | Bishop, Warren
1-00443149 Revision #1 Submitted | White River - Alderton #4 115 kV Line : Stewart Tap - Alderton OOS | 2017/10/31 08:00 | 2017/10/31 16:00 | PSE-TCC: Pending CISO-TCC: Pending | Bishop, Warren