## CROW - Outage Request Listing
CROW - Outage Request Listing
2016/10/20 13:13
Outage #/Revision/Status | Station/ Circuit/Equipment/ Path Description | Outage Start | Outage Complete | Required Approvals | Comments
1-00338541 Revision #5 Submitted | Tono Phase Shifting Bank OOS | 2015/12/18 12:00 | 2016/12/30 16:00 | PSE-TCC: Pending | Morse, Kenneth Excessive gas in oil.
1-00415646 Revision #1 Submitted | O'Brien - Long Lake 115 kV Line : Robinson Pt. Cable Sta. - Vashon OOS | 2016/10/17 07:00 | 2016/12/09 15:00 | PSE-TCC: Pending | Grieger, Lisa
1-00395214 Revision #4 Submitted | Blumaer - Saint Clair 115 kV Line : Blumaer - Saint Clair OOS | 2016/10/18 08:00 | 2016/10/21 17:00 | PSE-TCC: Pending | Kauer, Kaysee Getaways to new Spurgeon Creek Substation
1-00415706 Revision #1 Submitted | Sammamish 230/115kv Bank 2 OOS | 2016/10/19 07:00 | 2016/10/21 16:00 | PSE-TCC: Pending | Grieger, Lisa transformer maintenance
1-00405180 Revision #2 Submitted | Saint Clair 115kV 7524 BP & C OOS | 2016/10/20 12:00 | 2016/10/20 16:00 | PSE-TCC: Pending | McCulloch, Al J. Warranty Work
1-00405183 Revision #1 Submitted | Saint Clair 115kV 7525 BP & C OOS | 2016/10/20 13:00 | 2016/10/20 16:00 | PSE-TCC: Pending | McCulloch, Al J. Warranty Work
1-00405184 Revision #1 Submitted | Olympia 115kV 7455_L BP & C, Olympia 115kV 7455_M BP & C OOS | 2016/10/21 08:00 | 2016/10/21 12:00 | PSE-TCC: Pending | McCulloch, Al J. Warranty Work
1-00405177 Revision #2 Submitted | Saint Clair 115kV 946 BP & C OOS | 2016/10/21 12:00 | 2016/10/21 16:00 | PSE-TCC: Pending | McCulloch, Al J. Warranty Work