|  |  |
| --- | --- |
| Business Units: | All Business Units |
| Date Range: | from **2016/09/12** to **2017/09/13** |
| Generate By: | Control Center: PSE Generation Control Center, PSE Transmission Control Center |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTAGE REQUESTS | | | | | | | | |
| Outage #/ Revision/ Status | Station/ Circuit/Equipment | Requested Date Range/ Duration | From/To/Type | Required Approvals | Path(s) Affected | | | Requested By/ Reason/Priority |
| Path | OTC Impact | WECC OTC Seas. Ratings |
| 1-00390540 Revision #5 Submitted | Blumaer - Yelm 115 kV Line : Rainier View - Yelm YEL SW #7514 to RAI SW #7176 OOS | 2016/08/22 to 2016/09/29 38.38 Days | 07:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. re-conductor line |
| 1-00405756 Revision #3 Submitted | Olympia - Saint Clair #1 115 kV Line : Chambers - N.O. Sw 167 - Southwick CHA SW #377 to CHA HS SW #1227 to N.O. Pole SW #167 to SWI SW #578, Olympia - Saint Clair #1 115 kV Line : Southwick - Patterson CHA SW #377 to CHA HS SW #1227 to N.O. Pole SW #167 to SWI SW #578 OOS | 2016/08/25 to 2016/09/23 28.54 Days | 23:00 - 12:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Remove B/O phase blade from CHA SW #1263. Estimated return time to replace switch on another project. |
| 1-00401591 Revision #10 Submitted | Olympia - Saint Clair #1 115 kV Line : Chambers - N.O. Sw 167 - Southwick CHA SW #1263 to N.O. Pole SW #167 to SWI HS SW #7153 to PAT SW #940, Olympia - Saint Clair #1 115 kV Line : Southwick - Patterson CHA SW #1263 to N.O. Pole SW #167 to SWI HS SW #7153 to PAT SW #940 OOS | 2016/08/30 to 2016/09/16 17.33 Days | 00:00 - 08:00 Continuous | PSE-TCC: Pending |  |  |  | Thrasher, John Replace line switch 578. Future outage to continue into Chambers sub for SW #1263 replacement. |
| 1-00338541 Revision #5 Submitted | Tono Phase Shifting Bank OOS | 2015/12/18 to 2016/12/30 378.17 Days | 12:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | Morse, Kenneth Excessive gas in oil. |
| 1-00368671 Revision #2 Submitted | Lakeside Lakeside The Lakeside Auxiliary Bus to be cut out. OOS | 2016/05/12 to 2016/09/30 141.33 Days | 09:00 - 17:00 Continuous | PSE-TCC: Pending |  |  |  | Mitts, Corry The auxiliary bus from Lakeside PCBs 7078A - 320A - 252A - 306A - 808A - 127A - 25A - 257A - 307A - 297A - 276A - 359A to be cut out for long lining. |
| 1-00409172 Revision #1 Submitted | White River - Electron Heights #1 115 kV Line : Rhodes Lake - Knoble RHO SW #527 to KNO SW #7201 OOS | 2016/10/03 to 2016/10/21 18.38 Days | 07:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Transmission relocation |
| 1-00407836 Revision #2 Submitted | Plum Street 115kV 1048, Plum Street 115kV 1048\_L, Plum Street 115kV 1048\_M OOS | 2016/10/03 to 2016/10/03 60 Mins | 08:00 - 09:00 Continuous | PSE-TCC: Pending |  |  |  | Grieger, Lisa repair breaker |
| 1-00404569 Revision #1 Submitted | Portal Way - Lynden 115 kV Line : Berthusen - Lynden OOS | 2016/10/10 to 2016/10/13 3.33 Days | 08:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | Kauer, Kaysee circuit switcher replacement |
| 1-00395214 Revision #2 Submitted | Blumaer - Saint Clair 115 kV Line : Blumaer - Saint Clair OOS | 2016/10/17 to 2016/10/20 3.38 Days | 08:00 - 17:00 Continuous | PSE-TCC: Pending |  |  |  | Kauer, Kaysee Getaways to new Spurgeon Creek Substation |
| 1-00405166 Revision #2 Submitted | Saint Clair Capacitor Bank OOS | 2016/10/17 to 2016/10/17 4 Hours | 08:00 - 12:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Warranty work |
| 1-00375347 Revision #4 Submitted | Boeing Puyallup - Fredrickson 115 kV Line : Boeing Puyallup - Fredrickson OOS | 2016/10/17 to 2016/10/17 4 Hours | 08:30 - 12:30 Continuous | PSE-TCC: Pending |  |  |  | Mikelsen, Mike End to End testing |
| 1-00405173 Revision #1 Submitted | Saint Clair 115kV 948 BP & C OOS | 2016/10/17 to 2016/10/17 3 Hours | 13:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Warranty Work |
| 1-00392297 Revision #4 Submitted | Alderton - Electron Heights 115 kV Line: Rhodes Lake - Knoble OOS | 2016/10/18 to 2016/10/29 11.33 Days | 08:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | Thrasher, John Relocate line (7 poles and under build) |
| 1-00405176 Revision #2 Submitted | Saint Clair 115kV 945 BP & C OOS | 2016/10/18 to 2016/10/18 4 Hours | 08:00 - 12:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Warranty Work |
| 1-00405178 Revision #2 Submitted | Saint Clair 115kV 947 BP & C OOS | 2016/10/18 to 2016/10/18 3 Hours | 13:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Warranty Work |
| 1-00405180 Revision #2 Submitted | Saint Clair 115kV 7524 BP & C OOS | 2016/10/20 to 2016/10/20 4 Hours | 12:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Warranty Work |
| 1-00405183 Revision #1 Submitted | Saint Clair 115kV 7525 BP & C OOS | 2016/10/20 to 2016/10/20 3 Hours | 13:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Warranty Work |
| 1-00405184 Revision #1 Submitted | Olympia 115kV 7455\_L BP & C, Olympia 115kV 7455\_M BP & C OOS | 2016/10/21 to 2016/10/21 4 Hours | 08:00 - 12:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Warranty Work |
| 1-00405177 Revision #2 Submitted | Saint Clair 115kV 946 BP & C OOS | 2016/10/21 to 2016/10/21 4 Hours | 12:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Warranty Work |
| 1-00404595 Revision #1 Submitted | Lake Tradition 115kV 305\_L, Lake Tradition 115kV 305\_M OOS | 2016/10/26 to 2016/10/26 9 Hours | 07:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | Kauer, Kaysee Repair water leaks. |
| 1-00388539 Revision #2 Submitted | Moorlands - Vitulli 115 kV Line : Moorlands - Kenmore MOO PCB's 1272/1273 to KNM SW #726 OOS | 2016/09/06 to 2016/10/07 31.42 Days | 08:00 - 18:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Pole replacement and reconductor |
| 1-00409853 Revision #3 Submitted | Sedro Woolley - Bellingham #4 115 kV Line : Alger - Bellingham OOS | 2016/09/09 to 2016/09/12 2.73 Days | 22:24 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | Kauer, Kaysee repair broken cross arm, pole replacement |
| 1-00390789 Revision #4 Submitted | Lakeside - Lochleven 115 kV Line : South Bellevue - Lochleven LAK PCB 320 to SBE SW #952 OOS | 2016/09/12 to 2016/09/16 4.38 Days | 07:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Replace two poles with Glu-Lam |
| 1-00407531 Revision #1 Submitted | Shuffleton - Lakeside 115 kV Line : South Mercer Tap - Mercerwood Tap OOS | 2016/09/12 to 2016/09/16 4.42 Days | 08:00 - 18:00 Noncontinuous | PSE-TCC: Pending |  |  |  | Grieger, Lisa sw 778 to sw 98 cell site work |
| 1-00408852 Revision #4 Submitted | Miller Bay 115kV SW4300 MIL SW #'s 4300 to 4301 to MIL HS SW #7556, Miller Bay 115kV SW4301 OOS | 2016/09/13 to 2016/09/28 15.42 Days | 06:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. SPCC work in substation |
| 1-00404474 Revision #1 Submitted | Sumas - Bellingham 115 kV Line : Kendall - Nugents Corner OOS | 2016/09/13 to 2016/09/13 12.5 Hours | 06:30 - 19:00 Continuous | PSE-TCC: Pending |  |  |  | Kauer, Kaysee Changing out line CCVT and panel |
| 1-00388354 Revision #1 Submitted | White River 230/115kv Bank 1 WRT PCB 7395/7396 and PCB 144 main bus disconnects opened to facilitate NERC trip checks. OOS | 2016/09/13 to 2016/09/13 5 Hours | 09:00 - 14:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. NERC Trip Checks |
| 1-00410144 Revision #1 Submitted | Long Lake 115kV 7431\_M, Long Lake 115kV 985\_M, Long Lake 115kV 986\_M to LOL BK Low Side Disc. OOS | 2016/09/14 to 2016/09/14 7 Hours | 06:00 - 13:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Repairing BK HS SW #132 |
| 1-00409197 Revision #1 Submitted | White River 230/115kv Bank 2 WRT PCB 7399/7400 and PCB 402 main bus disconnects opened to facilitate NERC trip checks. OOS | 2016/09/14 to 2016/09/14 5 Hours | 09:00 - 14:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Nerc Trip Checks |
| 1-00407673 Revision #1 Submitted | Alderton - Electron Heights 115 kV Line: Rhodes Lake - Knoble RHO SW #527 to KNO SW #7201 OOS | 2016/09/15 to 2016/09/15 8 Hours | 07:00 - 15:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Install mobile sub. |
| 1-00404535 Revision #1 Submitted | Sumas - Lynden 115 kV Line : Lynden - Schuett OOS | 2016/09/15 to 2016/10/07 22.33 Days | 08:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | Kauer, Kaysee Changing out breaker |
| 1-00405849 Revision #1 Submitted | Snoqualmie - Lake Tradition #2 115 kV Line : Snoqualmie - Lake Tradition LTN PCB 961 to SNQ SW #1084 OOS | 2016/09/16 to 2016/09/16 9 Hours | 07:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Cell Site Work |
| 1-00410239 Revision #2 Submitted | Fredrickson - Gravelly Lake 115 kV Line: Tillicum Tap - Fredrickson FRS PCB 1332-L to GRV PCB 7130-L to TIL SW #814, Fredrickson - Gravelly Lake 115 kV Line: Tillicum Tap - Gravelly Lake OOS | 2016/09/19 to 2016/09/23 4.5 Days | 06:00 - 18:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. BPA pulling wire over the line |
| 1-00390735 Revision #1 Submitted | Valley Junction 115kV P4284 OOS | 2016/09/19 to 2016/09/20 1.38 Days | 07:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. SEL relay replacement |
| 1-00390790 Revision #6 Submitted | Lakeside - Mercer Island 115 kV Line : Factoria - Enatai Cable Station FAC SW #7274 to Pole SW #1288 OOS | 2016/09/19 to 2016/10/05 16.46 Days | 07:00 - 18:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Replaces poles and re-conductor |
| 1-00398904 Revision #1 Submitted | Poison Spring - Wind Ridge 230 kV line : Poison Springs - Wind Ridge OOS | 2016/09/19 to 2016/09/23 4.38 Days | 07:00 - 16:00 Noncontinuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Transfer trip Scheme 061 testing. Will trip all PCB's individually twice. |
| 1-00400491 Revision #1 Submitted | Whidbey - Greenbank #1 115 kV Line : Coupville - Greenbank GBK PCB 3232-L to CPV Pole SW # 3241 OOS | 2016/09/19 to 2016/09/23 4.5 Days | 07:00 - 19:00 Noncontinuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. |
| 1-00402204 Revision #7 Submitted | Bellingham - Roeder #1 115 kV Line : Bellingham - Old Town BHM PCB 492 to OLD SW #3047 OOS | 2016/09/19 to 2016/09/30 11.46 Days | 07:00 - 18:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. pole relocation |
| 1-00409157 Revision #1 Submitted | Lakeside - Goodes Corner 115 kV Line : Eastgate - Goodes Corner GOO PCB 7069-L to EGT SW #433 (Long Line C) OOS | 2016/09/19 to 2016/09/24 5.5 Days | 07:00 - 19:00 Noncontinuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Cell Site |
| 1-00398899 Revision #3 Submitted | Poison Spring - Wild Horse 230 kV line : Poison Springs - Wild Horse OOS | 2016/09/20 to 2016/09/20 9 Hours | 07:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Transfer Trip testing of Scheme 105. 2 sets of open and closes on the line and substation 230 kV PCB's |
| 1-00395943 Revision #2 Submitted | Sammamish - Novelty Hill #2 230 kV Line : Novelty Hill - Sammamish NOV PCB 7261-L&M OOS | 2016/09/20 to 2016/09/20 7 Hours | 08:00 - 15:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Significant Outage  Relay Trip Checks |
| 1-00397287 Revision #3 Submitted | SeaTac - Bow Lake 115 kV Line : SeaTac - Bow Lake ASB PCB 501 L&M to BOW PCB's 7107 & 7108 D1&2 OOS | 2016/09/20 to 2016/09/20 7 Hours | 09:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Relay testing and trip checks |
| 1-00401229 Revision #2 Submitted | O'Brien - Metro Renton 115 kV Line : O'Brien - Orillia OBR PCB 227-L&A to ORI SW #526, O'Brien - Midway #2 115 kV Line : O'Brien - Manhattan OBR PCB 226-L&A to MHT SW #18 OOS | 2016/09/21 to 2016/09/21 9 Hours | 07:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Proximity crane work for a foot bridge. |
| 1-00398896 Revision #3 Submitted | Wind Ridge Reactor WDR PCB 7179-M OOS | 2016/09/21 to 2016/09/21 8 Hours | 08:00 - 16:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Transfer Trip testing |
| 1-00340473 Revision #4 Submitted | South Bremerton - Long Lake #1 115 kV Line : South Bremerton - East Port Orchard Tap SBR PCB 7552-L&A to N.O. Pole SW #7155 to EPO SW #7427 OOS | 2016/09/22 to 2016/09/24 2.42 Days | 05:00 - 15:00 Continuous | PSE-TCC: Pending |  |  |  | Morse, Kenneth WA DOT fish culvert project |
| 1-00393638 Revision #4 Submitted | Whidbey - Greenbank #1 115 kV Line : Whidbey - Coupeville WBY PCB 635 to CPV SW #3227 OOS | 2016/09/25 to 2016/10/20 24.46 Days | 19:00 - 06:00 Continuous | PSE-TCC: Pending |  |  |  | Morse, Kenneth Replace 8 spans of conductors and poles. Line out from 8 PM to 5 AM nightly |
| 1-00409140 Revision #1 Submitted | White River - Krain Corner #2 115 kV Line: Bonney Lake - Krain Corner Tap BON SW #412 to Pole SW #902 OOS | 2016/09/26 to 2016/09/30 4.5 Days | 07:00 - 19:00 Noncontinuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. |
| 1-00410312 Revision #1 Submitted | Krain Corner - Enumclaw 115 kV Line : Enumclaw - Krain Corner KRA PCB 556-L&M OOS | 2016/09/27 to 2016/09/27 9 Hours | 09:00 - 18:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. NERC trip checks and relay maintenance |
| 1-00396757 Revision #8 Submitted | Sammamish - North Bellevue 115 kV Line : Northrup - Bridle Trails OOS | 2016/09/29 to 2016/09/29 10 Hours | 06:30 - 16:30 Continuous | PSE-TCC: Pending |  |  |  | Parker, David setting a distribution pole |
| 1-00409233 Revision #1 Submitted | Electron Heights - Boeing Puyallup 115 kV Line : Sunrise - Boeing Puyallup BOP PCB 1216-B to BOP SW #1213-A to SUN 7167 OOS | 2016/09/30 to 2016/09/30 8 Hours | 07:00 - 15:00 Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. Installing a down guy |