|  |  |
| --- | --- |
| Business Units: | All Business Units |
| Date Range: | from **2016/09/12** to **2017/09/13** |
| Generate By: | Control Center: PSE Generation Control Center, PSE Transmission Control Center |

|  |
| --- |
| OUTAGE REQUESTS |
| Outage #/Revision/Status | Station/Circuit/Equipment | Requested Date Range/Duration | From/To/Type | Required Approvals | Path(s) Affected | Requested By/Reason/Priority |
| Path | OTC Impact | WECC OTCSeas. Ratings |
| 1-00390540Revision #5Submitted | Blumaer - Yelm 115 kV Line : Rainier View - Yelm YEL SW #7514 to RAI SW #7176 OOS | 2016/08/22 to2016/09/2938.38 Days | 07:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.re-conductor line |
| 1-00405756Revision #3Submitted | Olympia - Saint Clair #1 115 kV Line : Chambers - N.O. Sw 167 - Southwick CHA SW #377 to CHA HS SW #1227 to N.O. Pole SW #167 to SWI SW #578, Olympia - Saint Clair #1 115 kV Line : Southwick - Patterson CHA SW #377 to CHA HS SW #1227 to N.O. Pole SW #167 to SWI SW #578 OOS | 2016/08/25 to2016/09/2328.54 Days | 23:00 - 12:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Remove B/O phase blade from CHA SW #1263. Estimated return time to replace switch on another project. |
| 1-00401591Revision #10Submitted | Olympia - Saint Clair #1 115 kV Line : Chambers - N.O. Sw 167 - Southwick CHA SW #1263 to N.O. Pole SW #167 to SWI HS SW #7153 to PAT SW #940, Olympia - Saint Clair #1 115 kV Line : Southwick - Patterson CHA SW #1263 to N.O. Pole SW #167 to SWI HS SW #7153 to PAT SW #940 OOS | 2016/08/30 to2016/09/1617.33 Days | 00:00 - 08:00Continuous | PSE-TCC: Pending |  |  |  | Thrasher, JohnReplace line switch 578. Future outage to continue into Chambers sub for SW #1263 replacement. |
| 1-00338541Revision #5Submitted | Tono Phase Shifting Bank OOS | 2015/12/18 to2016/12/30378.17 Days | 12:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | Morse, KennethExcessive gas in oil. |
| 1-00368671Revision #2Submitted | Lakeside Lakeside The Lakeside Auxiliary Bus to be cut out. OOS | 2016/05/12 to2016/09/30141.33 Days | 09:00 - 17:00Continuous | PSE-TCC: Pending |  |  |  | Mitts, CorryThe auxiliary bus from Lakeside PCBs 7078A - 320A - 252A - 306A - 808A - 127A - 25A - 257A - 307A - 297A - 276A - 359A to be cut out for long lining. |
| 1-00409172Revision #1Submitted | White River - Electron Heights #1 115 kV Line : Rhodes Lake - Knoble RHO SW #527 to KNO SW #7201 OOS | 2016/10/03 to2016/10/2118.38 Days | 07:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Transmission relocation |
| 1-00407836Revision #2Submitted | Plum Street 115kV 1048, Plum Street 115kV 1048\_L, Plum Street 115kV 1048\_M OOS | 2016/10/03 to2016/10/0360 Mins | 08:00 - 09:00Continuous | PSE-TCC: Pending |  |  |  | Grieger, Lisarepair breaker |
| 1-00404569Revision #1Submitted | Portal Way - Lynden 115 kV Line : Berthusen - Lynden OOS | 2016/10/10 to2016/10/133.33 Days | 08:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | Kauer, Kayseecircuit switcher replacement |
| 1-00395214Revision #2Submitted | Blumaer - Saint Clair 115 kV Line : Blumaer - Saint Clair OOS | 2016/10/17 to2016/10/203.38 Days | 08:00 - 17:00Continuous | PSE-TCC: Pending |  |  |  | Kauer, KayseeGetaways to new Spurgeon Creek Substation |
| 1-00405166Revision #2Submitted | Saint Clair Capacitor Bank OOS | 2016/10/17 to2016/10/174 Hours | 08:00 - 12:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Warranty work |
| 1-00375347Revision #4Submitted | Boeing Puyallup - Fredrickson 115 kV Line : Boeing Puyallup - Fredrickson OOS | 2016/10/17 to2016/10/174 Hours | 08:30 - 12:30Continuous | PSE-TCC: Pending |  |  |  | Mikelsen, MikeEnd to End testing |
| 1-00405173Revision #1Submitted | Saint Clair 115kV 948 BP & C OOS | 2016/10/17 to2016/10/173 Hours | 13:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Warranty Work |
| 1-00392297Revision #4Submitted | Alderton - Electron Heights 115 kV Line: Rhodes Lake - Knoble OOS | 2016/10/18 to2016/10/2911.33 Days | 08:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | Thrasher, JohnRelocate line (7 poles and under build) |
| 1-00405176Revision #2Submitted | Saint Clair 115kV 945 BP & C OOS | 2016/10/18 to2016/10/184 Hours | 08:00 - 12:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Warranty Work |
| 1-00405178Revision #2Submitted | Saint Clair 115kV 947 BP & C OOS | 2016/10/18 to2016/10/183 Hours | 13:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Warranty Work |
| 1-00405180Revision #2Submitted | Saint Clair 115kV 7524 BP & C OOS | 2016/10/20 to2016/10/204 Hours | 12:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Warranty Work |
| 1-00405183Revision #1Submitted | Saint Clair 115kV 7525 BP & C OOS | 2016/10/20 to2016/10/203 Hours | 13:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Warranty Work |
| 1-00405184Revision #1Submitted | Olympia 115kV 7455\_L BP & C, Olympia 115kV 7455\_M BP & C OOS | 2016/10/21 to2016/10/214 Hours | 08:00 - 12:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Warranty Work |
| 1-00405177Revision #2Submitted | Saint Clair 115kV 946 BP & C OOS | 2016/10/21 to2016/10/214 Hours | 12:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Warranty Work |
| 1-00404595Revision #1Submitted | Lake Tradition 115kV 305\_L, Lake Tradition 115kV 305\_M OOS | 2016/10/26 to2016/10/269 Hours | 07:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | Kauer, KayseeRepair water leaks. |
| 1-00388539Revision #2Submitted | Moorlands - Vitulli 115 kV Line : Moorlands - Kenmore MOO PCB's 1272/1273 to KNM SW #726 OOS | 2016/09/06 to2016/10/0731.42 Days | 08:00 - 18:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Pole replacement and reconductor |
| 1-00409853Revision #3Submitted | Sedro Woolley - Bellingham #4 115 kV Line : Alger - Bellingham OOS | 2016/09/09 to2016/09/122.73 Days | 22:24 - 16:00Continuous | PSE-TCC: Pending |  |  |  | Kauer, Kayseerepair broken cross arm, pole replacement |
| 1-00390789Revision #4Submitted | Lakeside - Lochleven 115 kV Line : South Bellevue - Lochleven LAK PCB 320 to SBE SW #952 OOS | 2016/09/12 to2016/09/164.38 Days | 07:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Replace two poles with Glu-Lam |
| 1-00407531Revision #1Submitted | Shuffleton - Lakeside 115 kV Line : South Mercer Tap - Mercerwood Tap OOS | 2016/09/12 to2016/09/164.42 Days | 08:00 - 18:00Noncontinuous | PSE-TCC: Pending |  |  |  | Grieger, Lisasw 778 to sw 98 cell site work |
| 1-00408852Revision #4Submitted | Miller Bay 115kV SW4300 MIL SW #'s 4300 to 4301 to MIL HS SW #7556, Miller Bay 115kV SW4301 OOS | 2016/09/13 to2016/09/2815.42 Days | 06:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.SPCC work in substation |
| 1-00404474Revision #1Submitted | Sumas - Bellingham 115 kV Line : Kendall - Nugents Corner OOS | 2016/09/13 to2016/09/1312.5 Hours | 06:30 - 19:00Continuous | PSE-TCC: Pending |  |  |  | Kauer, KayseeChanging out line CCVT and panel |
| 1-00388354Revision #1Submitted | White River 230/115kv Bank 1 WRT PCB 7395/7396 and PCB 144 main bus disconnects opened to facilitate NERC trip checks. OOS | 2016/09/13 to2016/09/135 Hours | 09:00 - 14:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.NERC Trip Checks |
| 1-00410144Revision #1Submitted | Long Lake 115kV 7431\_M, Long Lake 115kV 985\_M, Long Lake 115kV 986\_M to LOL BK Low Side Disc. OOS | 2016/09/14 to2016/09/147 Hours | 06:00 - 13:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Repairing BK HS SW #132 |
| 1-00409197Revision #1Submitted | White River 230/115kv Bank 2 WRT PCB 7399/7400 and PCB 402 main bus disconnects opened to facilitate NERC trip checks. OOS | 2016/09/14 to2016/09/145 Hours | 09:00 - 14:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Nerc Trip Checks |
| 1-00407673Revision #1Submitted | Alderton - Electron Heights 115 kV Line: Rhodes Lake - Knoble RHO SW #527 to KNO SW #7201 OOS | 2016/09/15 to2016/09/158 Hours | 07:00 - 15:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Install mobile sub. |
| 1-00404535Revision #1Submitted | Sumas - Lynden 115 kV Line : Lynden - Schuett OOS | 2016/09/15 to2016/10/0722.33 Days | 08:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | Kauer, KayseeChanging out breaker |
| 1-00405849Revision #1Submitted | Snoqualmie - Lake Tradition #2 115 kV Line : Snoqualmie - Lake Tradition LTN PCB 961 to SNQ SW #1084 OOS | 2016/09/16 to2016/09/169 Hours | 07:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Cell Site Work |
| 1-00410239Revision #2Submitted | Fredrickson - Gravelly Lake 115 kV Line: Tillicum Tap - Fredrickson FRS PCB 1332-L to GRV PCB 7130-L to TIL SW #814, Fredrickson - Gravelly Lake 115 kV Line: Tillicum Tap - Gravelly Lake OOS | 2016/09/19 to2016/09/234.5 Days | 06:00 - 18:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.BPA pulling wire over the line |
| 1-00390735Revision #1Submitted | Valley Junction 115kV P4284 OOS | 2016/09/19 to2016/09/201.38 Days | 07:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.SEL relay replacement |
| 1-00390790Revision #6Submitted | Lakeside - Mercer Island 115 kV Line : Factoria - Enatai Cable Station FAC SW #7274 to Pole SW #1288 OOS | 2016/09/19 to2016/10/0516.46 Days | 07:00 - 18:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Replaces poles and re-conductor |
| 1-00398904Revision #1Submitted | Poison Spring - Wind Ridge 230 kV line : Poison Springs - Wind Ridge OOS | 2016/09/19 to2016/09/234.38 Days | 07:00 - 16:00Noncontinuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Transfer trip Scheme 061 testing. Will trip all PCB's individually twice. |
| 1-00400491Revision #1Submitted | Whidbey - Greenbank #1 115 kV Line : Coupville - Greenbank GBK PCB 3232-L to CPV Pole SW # 3241 OOS | 2016/09/19 to2016/09/234.5 Days | 07:00 - 19:00Noncontinuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. |
| 1-00402204Revision #7Submitted | Bellingham - Roeder #1 115 kV Line : Bellingham - Old Town BHM PCB 492 to OLD SW #3047 OOS | 2016/09/19 to2016/09/3011.46 Days | 07:00 - 18:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.pole relocation |
| 1-00409157Revision #1Submitted | Lakeside - Goodes Corner 115 kV Line : Eastgate - Goodes Corner GOO PCB 7069-L to EGT SW #433 (Long Line C) OOS | 2016/09/19 to2016/09/245.5 Days | 07:00 - 19:00Noncontinuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Cell Site |
| 1-00398899Revision #3Submitted | Poison Spring - Wild Horse 230 kV line : Poison Springs - Wild Horse OOS | 2016/09/20 to2016/09/209 Hours | 07:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Transfer Trip testing of Scheme 105. 2 sets of open and closes on the line and substation 230 kV PCB's |
| 1-00395943Revision #2Submitted | Sammamish - Novelty Hill #2 230 kV Line : Novelty Hill - Sammamish NOV PCB 7261-L&M OOS | 2016/09/20 to2016/09/207 Hours | 08:00 - 15:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Significant Outage Relay Trip Checks |
| 1-00397287Revision #3Submitted | SeaTac - Bow Lake 115 kV Line : SeaTac - Bow Lake ASB PCB 501 L&M to BOW PCB's 7107 & 7108 D1&2 OOS | 2016/09/20 to2016/09/207 Hours | 09:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Relay testing and trip checks |
| 1-00401229Revision #2Submitted | O'Brien - Metro Renton 115 kV Line : O'Brien - Orillia OBR PCB 227-L&A to ORI SW #526, O'Brien - Midway #2 115 kV Line : O'Brien - Manhattan OBR PCB 226-L&A to MHT SW #18 OOS | 2016/09/21 to2016/09/219 Hours | 07:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Proximity crane work for a foot bridge. |
| 1-00398896Revision #3Submitted | Wind Ridge Reactor WDR PCB 7179-M OOS | 2016/09/21 to2016/09/218 Hours | 08:00 - 16:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Transfer Trip testing |
| 1-00340473Revision #4Submitted | South Bremerton - Long Lake #1 115 kV Line : South Bremerton - East Port Orchard Tap SBR PCB 7552-L&A to N.O. Pole SW #7155 to EPO SW #7427 OOS | 2016/09/22 to2016/09/242.42 Days | 05:00 - 15:00Continuous | PSE-TCC: Pending |  |  |  | Morse, KennethWA DOT fish culvert project |
| 1-00393638Revision #4Submitted | Whidbey - Greenbank #1 115 kV Line : Whidbey - Coupeville WBY PCB 635 to CPV SW #3227 OOS | 2016/09/25 to2016/10/2024.46 Days | 19:00 - 06:00Continuous | PSE-TCC: Pending |  |  |  | Morse, KennethReplace 8 spans of conductors and poles. Line out from 8 PM to 5 AM nightly |
| 1-00409140Revision #1Submitted | White River - Krain Corner #2 115 kV Line: Bonney Lake - Krain Corner Tap BON SW #412 to Pole SW #902 OOS | 2016/09/26 to2016/09/304.5 Days | 07:00 - 19:00Noncontinuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J. |
| 1-00410312Revision #1Submitted | Krain Corner - Enumclaw 115 kV Line : Enumclaw - Krain Corner KRA PCB 556-L&M OOS | 2016/09/27 to2016/09/279 Hours | 09:00 - 18:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.NERC trip checks and relay maintenance |
| 1-00396757Revision #8Submitted | Sammamish - North Bellevue 115 kV Line : Northrup - Bridle Trails OOS | 2016/09/29 to2016/09/2910 Hours | 06:30 - 16:30Continuous | PSE-TCC: Pending |  |  |  | Parker, Davidsetting a distribution pole |
| 1-00409233Revision #1Submitted | Electron Heights - Boeing Puyallup 115 kV Line : Sunrise - Boeing Puyallup BOP PCB 1216-B to BOP SW #1213-A to SUN 7167 OOS | 2016/09/30 to2016/09/308 Hours | 07:00 - 15:00Continuous | PSE-TCC: Pending |  |  |  | McCulloch, Al J.Installing a down guy |